## Cover Page
AMD Data Hygiene — QA Test Report v2
Frontend & UI Test Cases — post new-master-list merge
| Project | AMD Data Hygiene
| Version | 2.0 (new-master-list)
| Report Date | April 20, 2026
| Prepared By | QA Team
| Branch | quality-analysis / new-master-list
| Framework | React + Vite + Material UI
| Test Scope | UI / Frontend — All Components & Pages (v2 changes)
| Total TCs | 121
STATUS LEGEND
Not Run
Pass
Fail
Blocked
N/A
PRIORITY LEGEND
Critical
High
Medium
Low
KEY CHANGES vs v1
• Status filter 'Rejected' renamed to 'L0 Data' (API value unchanged)
• Card Status display: rejected records now show 'L0 Data'
• Card background now always white; differentiation via left border only
• On Hold color scheme changed from purple to yellow throughout
• RejectDialog removed — replaced by L0ConfirmDialog + DraftRecordDialog
• New action button: 'Submit Draft Record' (yellow) + 'Send to L0' (red)
• Draft dialog: dynamic fields, integer type support, history pre-fill
• Pending chip added to CorrectionsTable group header
• Groups auto-expand only for pending; others collapsed by default
• Draft Record section (read-only SuggestionRow) shown for On Hold groups
• SuggestionRow: internal keys filtered; showRadio prop added
• Editable field changed from 'coreCount' to 'cpu(s)'
• Route keys added to prevent stale state between list pages
• /completed/:id route removed

## Test Summary
Test Summary Dashboard — v2
Module | Not Run | Pass | Fail | Blocked | N/A | Total | % Pass
Navigation | 9 | 0 | 0 | 0 | 0 | 9 | 0%
List Pages | 10 | 0 | 0 | 0 | 0 | 10 | 0%
ListHeader | 10 | 0 | 0 | 0 | 0 | 10 | 0%
RecordList | 5 | 0 | 0 | 0 | 0 | 5 | 0%
RecordCard | 13 | 0 | 0 | 0 | 0 | 13 | 0%
DetailsPage | 8 | 0 | 0 | 0 | 0 | 8 | 0%
ExecutionInfoBox | 3 | 0 | 0 | 0 | 0 | 3 | 0%
CorrectionsTable | 28 | 0 | 0 | 0 | 0 | 28 | 0%
SuggestionRow | 9 | 0 | 0 | 0 | 0 | 9 | 0%
ChooseOtherValueDropdown | 6 | 0 | 0 | 0 | 0 | 6 | 0%
RejectDialog | 1 | 0 | 0 | 0 | 0 | 1 | 0%
L0ConfirmDialog | 1 | 0 | 0 | 0 | 0 | 1 | 0%
DraftRecordDialog | 1 | 0 | 0 | 0 | 0 | 1 | 0%
ErrorPage | 2 | 0 | 0 | 0 | 0 | 2 | 0%
Loader | 1 | 0 | 0 | 0 | 0 | 1 | 0%
Responsive | 3 | 0 | 0 | 0 | 0 | 3 | 0%
Cross-Browser | 3 | 0 | 0 | 0 | 0 | 3 | 0%
Performance | 4 | 0 | 0 | 0 | 0 | 4 | 0%
Accessibility | 4 | 0 | 0 | 0 | 0 | 4 | 0%
TOTAL | 121 | 0 | 0 | 0 | 0 | 121

## Test Cases
AMD Data Hygiene v2 — UI/Frontend Test Cases
TC ID | Module | Component | Test Case | Pre-conditions | Steps | Expected Result | Actual Result | Status | Priority | Remarks
¦ NAVIGATION
TC-NAV-01 | Navigation | Navbar | Logo 'AMD_DH' click navigates to '/' (landing page) | App loaded on any route | 1. Click the 'AMD_DH' logo in the top-left of the navbar | Route changes to '/'; page title shows 'Data Hygiene Dashboard' |  | Not Run | High
TC-NAV-02 | Navigation | Navbar | 'Active List' nav link navigates to /active | App loaded | 1. Click 'Active List' in the navbar | Route changes to '/active'; title shows 'My Active List' |  | Not Run | High
TC-NAV-03 | Navigation | Navbar | 'Completed List' nav link navigates to /completed | App loaded | 1. Click 'Completed List' | Route changes to '/completed'; title shows 'My Completed List' |  | Not Run | High
TC-NAV-04 | Navigation | Navbar | 'On Hold' nav link navigates to /on-hold | App loaded | 1. Click 'On Hold' | Route changes to '/on-hold'; title shows 'On Hold Records' |  | Not Run | High
TC-NAV-05 | Navigation | Navbar | Active route NavLink shows underline indicator | User is on /active | 1. Observe navbar links while on /active | 'Active List' has bottomBorder underline; others are dimmed (opacity 0.7) |  | Not Run | Medium
TC-NAV-06 | Navigation | Navbar | Navbar stays fixed at top on scroll | Any list page with many records | 1. Scroll down past the viewport height; 2. Observe navbar position | Navbar remains pinned to top (position: fixed; AppBar) |  | Not Run | Medium
TC-NAV-07 | Navigation | Routing | Routes use stable 'key' props — navigating between modes resets state | App loaded on any list page | 1. Go to /active; type in search; 2. Click 'Completed List' | State resets — search clears, filter resets (key prop forces remount per route) |  | Not Run | High | Old routes did not have key props; now they do
TC-NAV-08 | Navigation | Routing | /:id route opens DetailsPage for that record | A valid ExecutionId is known | 1. Navigate directly to /<valid-id> | DetailsPage loads with Execution Information and Corrections Table for that record |  | Not Run | High
TC-NAV-09 | Navigation | Routing | /completed/:id route removed — all details now use /:id | App loaded | 1. Navigate to /completed/<id> | Route does NOT match — should fall back (no separate completed/:id route exists anymore) |  | Not Run | Medium | Route removed in updated App.jsx
¦ LIST PAGES
TC-LST-01 | List Pages | Landing ('/') | Landing page renders 'Data Hygiene Dashboard' title | App at '/' | 1. Open '/' | H3 heading 'Data Hygiene Dashboard' visible below the navbar |  | Not Run | High
TC-LST-02 | List Pages | Landing ('/') | Landing shows status filter buttons: Pending, Accepted, L0 Data, On Hold | App at '/' | 1. Open '/' | Four filter buttons visible: Pending (orange), Accepted (green), L0 Data (red), On Hold (yellow) |  | Not Run | High | 'Rejected' is now labelled 'L0 Data' in the filter UI
TC-LST-03 | List Pages | Landing ('/') | Clicking 'L0 Data' filter fetches records with status=rejected | Landing page loaded | 1. Click 'L0 Data' filter button; 2. Observe API request | API called with status=rejected; list updates to show L0 Data records |  | Not Run | Critical | Filter label changed from 'Rejected' to 'L0 Data'; API value still 'rejected'
TC-LST-04 | List Pages | Landing ('/') | Filter toggle: clicking active filter deactivates it | A filter button is active | 1. Click the active filter button again | Filter deactivates; all records shown again |  | Not Run | High
TC-LST-05 | List Pages | Active ('/active') | Active list shows age filter buttons only | User on /active | 1. Open /active | Three age filter buttons visible: '< 3 Days' (green), '3 - 6 Days' (amber), '> 6 Days' (red); no status filters |  | Not Run | High
TC-LST-06 | List Pages | Active ('/active') | Age filter '<3 Days' sends age=green to API | /active loaded | 1. Click '< 3 Days'; 2. Check network request | API called with status=pending&age=green |  | Not Run | High
TC-LST-07 | List Pages | Completed ('/completed') | Completed list shows only Accepted and L0 Data filter buttons | User on /completed | 1. Open /completed | Only 'Accepted' and 'L0 Data' filter buttons shown (Pending and On Hold absent) |  | Not Run | High | allowedFilters restricts to [accepted, rejected]
TC-LST-08 | List Pages | Completed ('/completed') | Completed list default fetches status=accepted,rejected | User on /completed; no filter selected | 1. Open /completed; 2. Inspect API request | API called with status=accepted,rejected |  | Not Run | Critical
TC-LST-09 | List Pages | On Hold ('/on-hold') | On Hold list shows age filter buttons | User on /on-hold | 1. Open /on-hold | Age filter buttons visible; default API call uses status=On Hold |  | Not Run | High
TC-LST-10 | List Pages | Empty State | Empty state message varies by filter active state | Filter applied with 0 results | 1. Click a filter that returns no records | Shows 'No records match the selected filter.' |  | Not Run | High
¦ LISTHEADER
TC-HDR-01 | ListHeader | Search Bar | Search placeholder text is correct | Any list page loaded | 1. Click inside the search field without typing | Placeholder text: 'Search Execution ID, Type, or Category...' |  | Not Run | Low
TC-HDR-02 | ListHeader | Search Bar | Typing triggers debounced API call after 500ms | List page loaded | 1. Type 'AMD' quickly; 2. Wait 600ms | Single API call fires ~500ms after typing stops; spinner appears during debounce |  | Not Run | High
TC-HDR-03 | ListHeader | Search Bar | Search field renders with gray border (#747d8a) and rounded corners (8px) | Any list page | 1. Inspect search field styling | Field has border: '1px solid #747d8aff'; borderRadius: 8px |  | Not Run | Medium | Border styling updated from old version
TC-HDR-04 | ListHeader | Search Bar | CircularProgress spinner appears in search field end adornment while loading | List page; search triggered | 1. Start typing; observe before debounce fires | Small circular spinner (size=18) visible at right end of search field |  | Not Run | Medium
TC-HDR-05 | ListHeader | Filter Buttons | Filter button inactive state: white background, gray (#727579) border | Any list page; no filter active | 1. Observe filter buttons at rest | All filter buttons have white (#ffffff) background and gray (#727579ff) border |  | Not Run | Medium | Updated patchSx styling
TC-HDR-06 | ListHeader | Filter Buttons | Filter button active state: colored background, white text, colored shadow | A filter button is clicked | 1. Click any filter button | Background fills with activeBg color; text turns white; shadow appears |  | Not Run | High
TC-HDR-07 | ListHeader | Filter Buttons | Filter button hover: slight lift (translateY -1px) and border color change | List page loaded | 1. Hover over an inactive filter button | Button lifts 1px and border color changes to the filter's accent color |  | Not Run | Medium | Updated hover effect: -1px (was -2px)
TC-HDR-08 | ListHeader | Filter Buttons — Updated Labels | 'Rejected' filter renamed to 'L0 Data' on Landing and Completed pages | Landing or Completed page | 1. Observe status filter buttons | Button shows label 'L0 Data' (not 'Rejected'); clicking it queries status=rejected |  | Not Run | Critical | Key change in v2
TC-HDR-09 | ListHeader | Filter Buttons — Updated Labels | 'On Hold' button on Landing page now uses yellow (#ca8a04 / #dbbc23) color scheme | Landing page | 1. Observe the 'On Hold' filter button | On Hold button accent is yellow (#dbbc23 active, #ca8a04 border); was purple in v1 |  | Not Run | High | Color scheme changed from purple to yellow
TC-HDR-10 | ListHeader | Filter Buttons — Age | Age filter colors updated: <3 Days uses emerald green (#10b981 active) | /active or /on-hold page | 1. Click '< 3 Days' filter | Active state background is #10b981 (emerald green), dot turns white |  | Not Run | Medium | AGE_FILTERS colors refreshed in v2
¦ RECORDLIST
TC-VRL-01 | RecordList | Initial Load | Full-page Loader shown when list is empty and loading | Fresh page navigation | 1. Open any list page | Loader spinner shown immediately; disappears once first records arrive |  | Not Run | High
TC-VRL-02 | RecordList | Infinite Scroll | Scrolling near bottom loads next page of records | First page (50 records) loaded; more pages exist | 1. Scroll to near the bottom | Additional records appended; bottom loader briefly visible |  | Not Run | Critical
TC-VRL-03 | RecordList | Count Label | 'Total records: N' label shown when showCount is true | List page loaded | 1. Observe above the record list | 'Total records: <N>' displayed for pages with age or status filters |  | Not Run | Medium
TC-VRL-04 | RecordList | Row Heights | Accepted/Approved cards: height 100; pending cards: height 160 | Mixed-status list | 1. Compare card heights in a list with both accepted and pending records | Accepted cards visually shorter (no Inconsistent Fields section); pending cards taller |  | Not Run | Medium
TC-VRL-05 | RecordList | Empty State | Empty message shown when no records and not loading | Filter with 0 results | 1. Apply filter returning 0 records; 2. Wait for load to finish | Centered h6 message appears: 'No records match the selected filter.' |  | Not Run | High
¦ RECORDCARD
TC-RCD-01 | RecordCard | Display | Card displays ExecutionID, BenchmarkCategory, BenchmarkType, Status | List with records | 1. Observe any record card | All four data labels and values visible |  | Not Run | Critical
TC-RCD-02 | RecordCard | Status Label — L0 Data | Records with status='rejected' show 'L0 Data' as the status text on the card | List has a rejected record | 1. Find a record with Status='Rejected' | Card status field shows 'L0 Data' (not 'Rejected') — display renamed in RecordCard |  | Not Run | Critical | Key UX change in v2: record.Status === 'rejected' -> displays 'L0 Data'
TC-RCD-03 | RecordCard | Card Background | All cards have white (#ffffff) background regardless of status | List with mixed-status records | 1. Compare card backgrounds across statuses | All cards are #ffffff; differentiation comes from left border color only |  | Not Run | High | Background no longer uses status tinted colors; simplified to white
TC-RCD-04 | RecordCard | Card Border — Pending | Pending card has orange (#ffae00) left border (6px) and outer border (1.3px) | List with pending records | 1. Observe pending card borders | 6px left border (#ffae00); 1.3px full border (#ffae00); white background |  | Not Run | High
TC-RCD-05 | RecordCard | Card Border — Accepted | Accepted card has green (#10b981) border | List with accepted records | 1. Observe accepted card borders | Green (#10b981) 6px left border; 1.3px outer border |  | Not Run | High
TC-RCD-06 | RecordCard | Card Border — On Hold | On Hold card has yellow (#f1e60b) border | List with on-hold records | 1. Observe on-hold card borders | Yellow (#f1e60b) 6px left border; 1.3px full border |  | Not Run | High | Changed to yellow from purple in v2
TC-RCD-07 | RecordCard | Card Border — L0 Data (Rejected) | L0 Data (rejected) card has red (#ef4444) border | List with rejected records | 1. Find a record with Status=Rejected (shown as L0 Data) | Red (#ef4444) 6px left border |  | Not Run | High
TC-RCD-08 | RecordCard | Card Hover | Card hover: translateY(-4px) lift with shadow | Any list page | 1. Hover over a card | Card lifts 4px (was 4px scale in v1) and shows colored shadow; cursor changes to pointer |  | Not Run | Medium | Hover changed from scale(1.02) to translateY(-4px)
TC-RCD-09 | RecordCard | Inconsistent Fields | Non-completed records show Inconsistent Fields chip list | List has pending or on-hold records | 1. Observe a pending card | Divider below main info; red error chips listing invalid field names |  | Not Run | High
TC-RCD-10 | RecordCard | Suggestions Available Badge | Pending records with suggestions show 'Suggestions available' italic label | List has a pending record with suggestionsCount=true | 1. Find a pending card that has suggestions | Italic text 'Suggestions available' visible in the Inconsistent Fields section (space-between row with chips) |  | Not Run | High | New in v2: SuggestionsCount prop passed to InconsistentFieldsList
TC-RCD-11 | RecordCard | Suggestions Available Badge | Pending records without suggestions do NOT show 'Suggestions available' | Pending record with suggestionsCount=false | 1. Find a pending card with no suggestions | No 'Suggestions available' label present |  | Not Run | High
TC-RCD-12 | RecordCard | Accepted/Approved | Accepted/Approved cards do NOT show Inconsistent Fields section | List with accepted records | 1. Find accepted card | No divider or chip list below main info row |  | Not Run | High
TC-RCD-13 | RecordCard | Navigation | Clicking a card navigates to DetailsPage for that record | List with records | 1. Click any card | Route changes to /<ExecutionId>; DetailsPage loads |  | Not Run | Critical
¦ DETAILSPAGE
TC-DET-01 | DetailsPage | Loading | Full Loader shown while fetching record details | User clicks a record card | 1. Click a card; observe immediately | Full-page Loader spinner shown until data arrives |  | Not Run | High
TC-DET-02 | DetailsPage | Error Handling | ErrorPage with Retry shown on API failure | API unreachable | 1. Simulate API failure; open a record | ErrorPage component renders with error message and Retry button |  | Not Run | High
TC-DET-03 | DetailsPage | Fallback | Plain text fallback if executionData is null | API returns no execution_details | 1. Response has no execution_details field | Text 'No execution data to show' rendered (not a crash) |  | Not Run | Medium
TC-DET-04 | DetailsPage | Snackbar — Success | Green success snackbar appears at top-center after accepting a suggestion | DetailsPage with pending corrections | 1. Select suggestion; 2. Click Accept; 3. Confirm in dialog | Snackbar: 'Data accepted successfully' — green filled, top-center |  | Not Run | Critical
TC-DET-05 | DetailsPage | Snackbar — Error | Red error snackbar appears on API failure during accept | Accept API returns error | 1. Simulate API error; attempt accept | Red snackbar with API error message |  | Not Run | High
TC-DET-06 | DetailsPage | Snackbar — Draft | Success snackbar shown after successful draft record submission | DetailsPage; draft dialog open | 1. Fill draft form; submit | Green snackbar: 'Draft record submitted successfully' |  | Not Run | High | New flow in v2
TC-DET-07 | DetailsPage | Snackbar — L0 | Success snackbar shown after sending to L0 | L0 confirm dialog triggered | 1. Click 'Send to L0'; confirm | Green snackbar: 'Rejected due to L0 data' |  | Not Run | High
TC-DET-08 | DetailsPage | Snackbar | Snackbar auto-dismisses after 3 seconds | Any snackbar visible | 1. Trigger any action snackbar; wait 3s | Snackbar disappears automatically |  | Not Run | Medium
¦ EXECUTIONINFOBOX
TC-EIB-01 | ExecutionInfoBox | Layout | Execution info displays in a 3-column grid on desktop | DetailsPage loaded | 1. Open a record's detail page on desktop | ExecutionInfoBox shows 3 fields per row |  | Not Run | High
TC-EIB-02 | ExecutionInfoBox | Layout | Grid collapses to single column on mobile (<md breakpoint) | Mobile viewport | 1. Resize to 375px width | Fields stack vertically |  | Not Run | Medium
TC-EIB-03 | ExecutionInfoBox | Display | Null/undefined field values display as '-' | Record with some null fields | 1. Open record with null execution info fields | Null values show '-' (hyphen) |  | Not Run | Medium
¦ CORRECTIONSTABLE
TC-COR-01 | CorrectionsTable | Empty State | Shows 'No invalid fields found.' when data is empty | Record with no invalid fields | 1. Open a fully-clean record | Centered gray text 'No invalid fields found.' shown |  | Not Run | High
TC-COR-02 | CorrectionsTable | Group Expansion | Pending groups auto-expand; non-pending groups auto-collapse on load | DetailsPage loaded with mixed-status groups | 1. Open a record with both pending and accepted groups | Pending groups are expanded; accepted/on-hold/L0 groups are collapsed by default |  | Not Run | Critical | New in v2: expandedGroups initialized based on isPending status
TC-COR-03 | CorrectionsTable | Group Accordion | Clicking collapsed group header expands it | A group is collapsed | 1. Click on the group header | Group body expands with collapse animation; icon changes to ExpandLess |  | Not Run | High
TC-COR-04 | CorrectionsTable | Group Accordion | Clicking expanded group header collapses it | A group is expanded | 1. Click on the group header | Group body collapses; icon changes to ExpandMore |  | Not Run | High
TC-COR-05 | CorrectionsTable | Status Chips — Pending | 'Pending' chip shown in group header for pending/invalid fields | A pending group | 1. Open a pending record, look at group header | Orange 'Pending' chip visible (#fff7ed background, #9a3412 text) |  | Not Run | High | New in v2: Pending chip added to group header
TC-COR-06 | CorrectionsTable | Status Chips — L0 Data | 'L0 Data' red chip in header when field status is 'l0 data' | Record with L0 data field | 1. Open record with L0 field | Red 'L0 Data' chip (#fef2f2 bg, #dc2626 text, #fca5a5 border) in header |  | Not Run | Medium
TC-COR-07 | CorrectionsTable | Status Chips — On Hold | 'On Hold' chip is now yellow (not purple) in header | Record with On Hold field | 1. Open on-hold record group header | Yellow 'On Hold' chip (#fef9c3 bg, #ca8a04 text, #fde047 border) |  | Not Run | High | Color changed from purple to yellow in v2
TC-COR-08 | CorrectionsTable | Status Chips — Accepted | 'Accepted' chip + 'Suggestion Selected'/'Custom...' chip shown for accepted fields | Record with accepted correction | 1. Open accepted group header | Green 'Accepted' chip and secondary chip indicating selection type |  | Not Run | High
TC-COR-09 | CorrectionsTable | Suggestions Header | 'Suggestions' label only shown when suggestions exist; includes italic hint for pending | Pending group with suggestions | 1. Open pending group with suggestions | Label reads: 'Suggestions (Hover over an option to see confidence score)' |  | Not Run | Medium | New hint text added in v2
TC-COR-10 | CorrectionsTable | Suggestions Header | Hints text NOT shown for accepted/on-hold groups | Accepted group with suggestions | 1. Open accepted group | No italic hint text in the Suggestions label |  | Not Run | Medium
TC-COR-11 | CorrectionsTable | Draft Records Section | Draft Record section shown below suggestions when group.draft_records exists | On Hold record with draft data | 1. Open an on-hold record that has a draft_records object | 'Draft Record' label and a read-only SuggestionRow (no radio) displayed with ON_HOLD_THEME |  | Not Run | Critical | New in v2: draft_records display for On Hold fields
TC-COR-12 | CorrectionsTable | Draft Records Section | Draft Record SuggestionRow has no radio button (showRadio=false) | On Hold record with draft data | 1. Inspect Draft Record row | No radio button on the left; row is read-only display |  | Not Run | High | showRadio prop newly added in v2
TC-COR-13 | CorrectionsTable | Draft Records Section | VM draft records show History CPU(s) value override | VM record, On Hold, with CPU history change | 1. Open VM on-hold record with CPU(s) history | Draft record SuggestionRow shows CPU(s) value from history, not from draft_records |  | Not Run | High | VM CPU(s) override logic applied to draft display
TC-COR-14 | CorrectionsTable | Action Buttons | Three action buttons shown for pending groups: Accept, Submit Draft Record, Send to L0 | Pending group; no suggestion selected | 1. Open pending group, observe action bar | Green 'Accept', yellow 'Submit Draft Record', red 'Send to L0' buttons visible |  | Not Run | Critical | Old 'Reject All' replaced by two separate actions in v2
TC-COR-15 | CorrectionsTable | Action Buttons | 'Accept' button disabled when no suggestion selected | Pending group, nothing selected | 1. Observe Accept button | Accept button is disabled (grayed out) |  | Not Run | Critical
TC-COR-16 | CorrectionsTable | Action Buttons | 'Submit Draft Record' and 'Send to L0' disabled when a suggestion IS selected | A suggestion is selected | 1. Select any suggestion; observe the other two buttons | Submit Draft Record and Send to L0 are disabled |  | Not Run | Critical | Mirrors old 'Reject All' disabled logic
TC-COR-17 | CorrectionsTable | Action Buttons | All action buttons hidden for non-pending fields | Accepted/On Hold/L0 field group | 1. Open non-pending group | No action button bar rendered |  | Not Run | High
TC-COR-18 | CorrectionsTable | Accept Confirm Dialog | Clicking Accept opens 'Confirm Accept' dialog | Suggestion selected in pending group | 1. Click 'Accept' | Dialog opens with green check icon, field name highlighted, Cancel and 'Yes, Accept' buttons |  | Not Run | Critical
TC-COR-19 | CorrectionsTable | Accept Confirm Dialog | 'Yes, Accept' shows spinner + 'Accepting...' while API is in-flight | Confirm dialog open | 1. Click 'Yes, Accept' | Button shows CircularProgress spinner with 'Accepting...' text; button disabled |  | Not Run | High
TC-COR-20 | CorrectionsTable | L0 Confirm Dialog | Clicking 'Send to L0' opens standalone L0 Confirm dialog | No suggestion selected; Send to L0 enabled | 1. Click 'Send to L0' | Dialog: 'Confirm Send to L0', warning amber icon, 'Yes, Confirm' (warning color) and Cancel |  | Not Run | Critical | L0 dialog now standalone in CorrectionsTable (not nested in RejectDialog)
TC-COR-21 | CorrectionsTable | L0 Confirm Dialog | L0 dialog: clicking X or Cancel during submission is disabled | L0 submission in progress | 1. Click 'Yes, Confirm'; immediately try to close | Dialog cannot be closed while submitting (disabled state) |  | Not Run | High
TC-COR-22 | CorrectionsTable | Draft Dialog | Clicking 'Submit Draft Record' opens Draft Record dialog with dynamic fields | No suggestion selected; Submit Draft enabled | 1. Click 'Submit Draft Record' | Dialog opens titled 'Submit Draft Record'; spinner shown while fields load from API; fields appear after |  | Not Run | Critical
TC-COR-23 | CorrectionsTable | Draft Dialog | Draft dialog pre-fills field values from history changes | Record with history data for the field | 1. Open Draft dialog for a field that has history | Form fields pre-populated with history values (from buildDisplayObjectFromChanges) |  | Not Run | High | New in v2: draftInitialValues from history
TC-COR-24 | CorrectionsTable | Draft Dialog | Integer-type fields render as number inputs with step=1, min=0 | Draft dialog open with integer fields | 1. Open draft dialog; inspect integer fields | Text field type='number', inputProps step=1 min=0; label shows '(integer)' hint |  | Not Run | High | New in v2: integer fields get type=number
TC-COR-25 | CorrectionsTable | Draft Dialog | Submit disabled until all fields are non-empty | Draft dialog with empty fields | 1. Observe Submit button | Submit button disabled; enables only after all fields have non-whitespace values |  | Not Run | High
TC-COR-26 | CorrectionsTable | Draft Dialog | Integer validation: error snackbar if non-integer value entered in integer field | Draft dialog; integer field present | 1. Type '2.5' in an integer field; 2. Click Submit | Error snackbar: 'The following fields require whole-number (integer) values: <fieldname>' |  | Not Run | High | New in v2: client-side integer validation before submit
TC-COR-27 | CorrectionsTable | Draft Dialog | 'Submit Draft Record' payload sets currentStatus='On Hold' | Draft form filled and submitted | 1. Submit a valid draft form; 2. Inspect API payload | POST to /draft-records/<field> with execution_id, form values, currentStatus='On Hold' |  | Not Run | High
TC-COR-28 | CorrectionsTable | VM CPU(s) Override | For VM sutType, accepted suggestion shows CPU(s) from history (not suggestion raw data) | VM record, suggestion selected, CPU(s) in history | 1. Select suggestion in VM record with CPU(s) history | CPU(s) field in SuggestionRow shows history value, displayed correctly |  | Not Run | High | getHistoryChangesForField logic; UI override in CorrectionsTable
¦ SUGGESTIONROW
TC-SGR-01 | SuggestionRow | Selection | Clicking a suggestion selects it; radio checked, row highlighted | Pending group with suggestions | 1. Click any suggestion row | Radio checked; border and background change to SELECTED theme (blue) |  | Not Run | Critical
TC-SGR-02 | SuggestionRow | Selection | Clicking selected suggestion deselects it | Suggestion selected | 1. Click the selected suggestion | Radio unchecked; row returns to white background |  | Not Run | High
TC-SGR-03 | SuggestionRow | Confidence Tooltip | Hovering over suggestion shows 'Confidence: X%' tooltip | Pending suggestion with score field | 1. Hover over a suggestion row | Tooltip appears: 'Confidence: X%' |  | Not Run | Medium
TC-SGR-04 | SuggestionRow | Internal Fields Filtered | Fields _id, execution_id, snapshot_id, search_key are hidden from suggestion display | Suggestion has these internal fields | 1. Open a suggestion row that has internal fields in data | None of _id, execution_id, snapshot_id, search_key appear as visible columns |  | Not Run | High | New in v2: internalKeys filter replaces old deduplication approach
TC-SGR-05 | SuggestionRow | showRadio prop | Draft Record SuggestionRow renders without radio button (showRadio=false) | On Hold group with draft record | 1. Observe Draft Record row | No radio button column on the left side of the row |  | Not Run | High | New showRadio prop in v2
TC-SGR-06 | SuggestionRow | EditableField — CPU(s) | CPU(s) field shows edit icon for VM sutType when suggestion selected | VM record; suggestion selected with CPU(s) field | 1. Select suggestion in VM record group | Pencil edit icon visible next to the CPU(s) value |  | Not Run | High | Field changed from 'coreCount' to 'cpu(s)' in v2
TC-SGR-07 | SuggestionRow | EditableField — CPU(s) | Inline edit: click pencil, change value, press Enter to save | CPU(s) edit icon visible | 1. Click pencil; change value; press Enter | New value shown; edit mode exits; value saved to editedSuggestions state |  | Not Run | High
TC-SGR-08 | SuggestionRow | EditableField — CPU(s) | Press Escape cancels inline edit and restores original value | Inline edit active | 1. Click pencil; change value; press Escape | Original value restored; input closed |  | Not Run | High
TC-SGR-09 | SuggestionRow | Accepted/OnHold State | Non-pending suggestion rows are read-only (opacity 0.5, cursor not-allowed) | Accepted group | 1. Open accepted group, view suggestions | All suggestions dimmed (opacity 0.5); clicking does nothing (cursor: not-allowed) |  | Not Run | High
¦ CHOOSEOTHERVALUEDROPDOWN
TC-CVD-01 | ChooseOtherValueDropdown | Visibility | Dropdown visible only for pending groups | Pending field group open | 1. Expand a pending group | Autocomplete dropdown 'Choose other <field>:' is present |  | Not Run | High
TC-CVD-02 | ChooseOtherValueDropdown | Visibility | Dropdown hidden for non-pending groups | Accepted group | 1. Expand an accepted group | No dropdown rendered (isPending=false -> returns null) |  | Not Run | High
TC-CVD-03 | ChooseOtherValueDropdown | Options | Opening dropdown fetches unique masterlist values | Pending group dropdown | 1. Click/open the autocomplete | Spinner appears; unique values from /unique-values API loaded as autocomplete options |  | Not Run | High
TC-CVD-04 | ChooseOtherValueDropdown | Selection | Selecting a value triggers metadata fetch and renders custom SuggestionRow | Dropdown with options loaded | 1. Select a value | Dropdown row border turns accent color; 'Custom Value' label appears; SuggestionRow with fetched metadata shown |  | Not Run | Critical
TC-CVD-05 | ChooseOtherValueDropdown | Clear | Clearing autocomplete clears custom suggestion | Custom value selected | 1. Clear the autocomplete (X button) | Custom SuggestionRow disappears; selection deactivated |  | Not Run | High
TC-CVD-06 | ChooseOtherValueDropdown | Theme Prop | Dropdown receives theme prop and applies activeTheme colors when selected | Custom value selected in pending group | 1. Select a custom value | Dropdown row uses SELECTED theme border/background colors |  | Not Run | Medium | New theme prop passed in v2
¦ REJECTDIALOG
TC-RJD-01 | RejectDialog | Removed | RejectDialog component no longer exists as a separate file | Components directory | 1. Check src/components/CorrectionsTableComponents/ directory | RejectDialog.jsx is NOT present; useRejectDialog.js hook is also removed |  | Not Run | Critical | BREAKING CHANGE: RejectDialog replaced by L0ConfirmDialog + DraftRecordDialog in v2
¦ L0CONFIRMDIALOG
TC-RJD-02 | L0ConfirmDialog | Standalone L0 Flow | L0 flow is now a direct dialog from the main action button bar | Pending group; no suggestion selected | 1. Click 'Send to L0'; 2. Observe dialog | Single-step confirmation dialog (no multi-step choose flow); directly confirms L0 send |  | Not Run | Critical
¦ DRAFTRECORDDIALOG
TC-RJD-03 | DraftRecordDialog | Standalone Draft Flow | Draft flow is now a direct dialog from the main action button bar | Pending group; no suggestion selected | 1. Click 'Submit Draft Record'; 2. Observe dialog | Direct Draft Record form dialog (no intermediate choose step) |  | Not Run | Critical
¦ ERRORPAGE
TC-ERR-01 | ErrorPage | Display | ErrorPage renders with error message | API error during list load | 1. Simulate API error; open list page | ErrorPage renders with the error.message and a Retry button |  | Not Run | High
TC-ERR-02 | ErrorPage | Retry | Retry button on ErrorPage triggers re-fetch | ErrorPage visible | 1. Click Retry | Fetch is re-triggered; if API healthy, list loads normally |  | Not Run | High
¦ LOADER
TC-LDR-01 | Loader | Spinner | Loader renders centered spinner in all loading states | Any loading condition | 1. Trigger loading (page load, record click, etc.) | Centered CircularProgress spinner visible; no layout breakage |  | Not Run | Medium
¦ RESPONSIVE
TC-RES-01 | Responsive | Mobile (<768px) | Search bar adapts to 90% width on mobile | Mobile viewport | 1. Resize to 375px; observe search field | Width is ~90% of viewport; no overflow |  | Not Run | High
TC-RES-02 | Responsive | Mobile (<768px) | Filter buttons wrap on narrow viewports | Mobile viewport with filters shown | 1. Open /active on mobile | Filter buttons wrap to next line; no horizontal scrollbar |  | Not Run | High
TC-RES-03 | Responsive | Tablet (768-1200px) | Record cards at 65vw readable on tablet | Tablet viewport | 1. Open list page at 768px wide | Cards at 65vw; text not clipped; cards centered |  | Not Run | Medium
¦ CROSS-BROWSER
TC-CBR-01 | Cross-Browser | Chrome | App renders and all flows work on Chrome (latest) | Chrome latest installed | 1. Open app in Chrome; test all main flows | No rendering issues; all dialogs and cards render correctly |  | Not Run | Critical
TC-CBR-02 | Cross-Browser | Firefox | App works correctly on Firefox (latest) | Firefox installed | 1. Open in Firefox; test main flows | No issues |  | Not Run | High
TC-CBR-03 | Cross-Browser | Edge | App works on Microsoft Edge | Edge installed | 1. Open app in Edge | No rendering or functionality issues |  | Not Run | Medium
¦ PERFORMANCE
TC-PER-01 | Performance | Load Time | List page shows first 50 records within 3 seconds | Fresh page load; backend running | 1. Open /active; time to first record render | Records visible within 3 seconds |  | Not Run | High
TC-PER-02 | Performance | Search Debounce | Results update within 1 second after 500ms debounce | List page loaded | 1. Type in search; wait for debounce | API fires once; results update within 1s of debounce completing |  | Not Run | High
TC-PER-03 | Performance | Memory / Abort | Navigating between list pages aborts stale in-flight requests | Rapidly switching routes | 1. Quickly switch between /active and /completed several times | Only current page results shown; no ghost data; no console AbortError crashes |  | Not Run | High
TC-PER-04 | Performance | Animation Smoothness | Card hover and filter button transitions are smooth (no jank) | Any list page | 1. Rapidly hover over cards and filter buttons | Transitions feel smooth; no flickering or layout shift |  | Not Run | Medium
¦ ACCESSIBILITY
TC-ACC-01 | Accessibility | Keyboard | Search field focusable via Tab key | Any list page | 1. Tab to search; type query | Focus indicator visible; search works via keyboard |  | Not Run | High
TC-ACC-02 | Accessibility | Keyboard | Filter buttons activatable via keyboard (Space/Enter) | List page with filters | 1. Tab to filter button; press Space or Enter | Filter activates; list updates |  | Not Run | High
TC-ACC-03 | Accessibility | Contrast | All text meets WCAG AA contrast ratio (>=4.5:1) | Any page | 1. Run Lighthouse accessibility audit | All text passes AA contrast |  | Not Run | Medium
TC-ACC-04 | Accessibility | ARIA | Dialogs have ARIA role and focus trap | Any dialog open | 1. Open Accept, L0, or Draft dialog; check ARIA | role='dialog'; focus trapped inside dialog while open |  | Not Run | Medium

## Bug Tracker
Bug Tracker
Bug ID | TC ID | Module | Component | Bug Title | Description | Severity | Priority | Status | Reported By | Reported Date | Fixed By | Fixed Date | Remarks
[6 empty] | [Blocker/Critical/Major/Minor/Trivial] |  | [Open/In Progress/Fixed/Verified/Closed]

## Execution Log
Test Execution Log
Run # | Date | Tester | Environment | Build/Branch | TCs Run | Passed | Failed | Blocked | Not Run | Pass % | Notes
1 | 2026-04-20 |  | Local Dev | quality-analysis/new-master-list | 121 | 0 | 0 | 0 | 121 | 0% | Initial run v2 — all TCs pending

## Navigation
Navigation — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-NAV-01 | Navbar | Logo 'AMD_DH' click navigates to '/' (landing page) | 1. Click the 'AMD_DH' logo in the top-left of the navbar | Route changes to '/'; page title shows 'Data Hygiene Dashboard' | Not Run | High
TC-NAV-02 | Navbar | 'Active List' nav link navigates to /active | 1. Click 'Active List' in the navbar | Route changes to '/active'; title shows 'My Active List' | Not Run | High
TC-NAV-03 | Navbar | 'Completed List' nav link navigates to /completed | 1. Click 'Completed List' | Route changes to '/completed'; title shows 'My Completed List' | Not Run | High
TC-NAV-04 | Navbar | 'On Hold' nav link navigates to /on-hold | 1. Click 'On Hold' | Route changes to '/on-hold'; title shows 'On Hold Records' | Not Run | High
TC-NAV-05 | Navbar | Active route NavLink shows underline indicator | 1. Observe navbar links while on /active | 'Active List' has bottomBorder underline; others are dimmed (opacity 0.7) | Not Run | Medium
TC-NAV-06 | Navbar | Navbar stays fixed at top on scroll | 1. Scroll down past the viewport height; 2. Observe navbar position | Navbar remains pinned to top (position: fixed; AppBar) | Not Run | Medium
TC-NAV-07 | Routing | Routes use stable 'key' props — navigating between modes resets state | 1. Go to /active; type in search; 2. Click 'Completed List' | State resets — search clears, filter resets (key prop forces remount per route) | Not Run | High | Old routes did not have key props; now they do
TC-NAV-08 | Routing | /:id route opens DetailsPage for that record | 1. Navigate directly to /<valid-id> | DetailsPage loads with Execution Information and Corrections Table for that record | Not Run | High
TC-NAV-09 | Routing | /completed/:id route removed — all details now use /:id | 1. Navigate to /completed/<id> | Route does NOT match — should fall back (no separate completed/:id route exists anymore) | Not Run | Medium | Route removed in updated App.jsx

## List_Pages
List Pages — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-LST-01 | Landing ('/') | Landing page renders 'Data Hygiene Dashboard' title | 1. Open '/' | H3 heading 'Data Hygiene Dashboard' visible below the navbar | Not Run | High
TC-LST-02 | Landing ('/') | Landing shows status filter buttons: Pending, Accepted, L0 Data, On Hold | 1. Open '/' | Four filter buttons visible: Pending (orange), Accepted (green), L0 Data (red), On Hold (yellow) | Not Run | High | 'Rejected' is now labelled 'L0 Data' in the filter UI
TC-LST-03 | Landing ('/') | Clicking 'L0 Data' filter fetches records with status=rejected | 1. Click 'L0 Data' filter button; 2. Observe API request | API called with status=rejected; list updates to show L0 Data records | Not Run | Critical | Filter label changed from 'Rejected' to 'L0 Data'; API value still 'rejected'
TC-LST-04 | Landing ('/') | Filter toggle: clicking active filter deactivates it | 1. Click the active filter button again | Filter deactivates; all records shown again | Not Run | High
TC-LST-05 | Active ('/active') | Active list shows age filter buttons only | 1. Open /active | Three age filter buttons visible: '< 3 Days' (green), '3 - 6 Days' (amber), '> 6 Days' (red); no status filters | Not Run | High
TC-LST-06 | Active ('/active') | Age filter '<3 Days' sends age=green to API | 1. Click '< 3 Days'; 2. Check network request | API called with status=pending&age=green | Not Run | High
TC-LST-07 | Completed ('/completed') | Completed list shows only Accepted and L0 Data filter buttons | 1. Open /completed | Only 'Accepted' and 'L0 Data' filter buttons shown (Pending and On Hold absent) | Not Run | High | allowedFilters restricts to [accepted, rejected]
TC-LST-08 | Completed ('/completed') | Completed list default fetches status=accepted,rejected | 1. Open /completed; 2. Inspect API request | API called with status=accepted,rejected | Not Run | Critical
TC-LST-09 | On Hold ('/on-hold') | On Hold list shows age filter buttons | 1. Open /on-hold | Age filter buttons visible; default API call uses status=On Hold | Not Run | High
TC-LST-10 | Empty State | Empty state message varies by filter active state | 1. Click a filter that returns no records | Shows 'No records match the selected filter.' | Not Run | High

## ListHeader
ListHeader — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-HDR-01 | Search Bar | Search placeholder text is correct | 1. Click inside the search field without typing | Placeholder text: 'Search Execution ID, Type, or Category...' | Not Run | Low
TC-HDR-02 | Search Bar | Typing triggers debounced API call after 500ms | 1. Type 'AMD' quickly; 2. Wait 600ms | Single API call fires ~500ms after typing stops; spinner appears during debounce | Not Run | High
TC-HDR-03 | Search Bar | Search field renders with gray border (#747d8a) and rounded corners (8px) | 1. Inspect search field styling | Field has border: '1px solid #747d8aff'; borderRadius: 8px | Not Run | Medium | Border styling updated from old version
TC-HDR-04 | Search Bar | CircularProgress spinner appears in search field end adornment while loading | 1. Start typing; observe before debounce fires | Small circular spinner (size=18) visible at right end of search field | Not Run | Medium
TC-HDR-05 | Filter Buttons | Filter button inactive state: white background, gray (#727579) border | 1. Observe filter buttons at rest | All filter buttons have white (#ffffff) background and gray (#727579ff) border | Not Run | Medium | Updated patchSx styling
TC-HDR-06 | Filter Buttons | Filter button active state: colored background, white text, colored shadow | 1. Click any filter button | Background fills with activeBg color; text turns white; shadow appears | Not Run | High
TC-HDR-07 | Filter Buttons | Filter button hover: slight lift (translateY -1px) and border color change | 1. Hover over an inactive filter button | Button lifts 1px and border color changes to the filter's accent color | Not Run | Medium | Updated hover effect: -1px (was -2px)
TC-HDR-08 | Filter Buttons — Updated Labels | 'Rejected' filter renamed to 'L0 Data' on Landing and Completed pages | 1. Observe status filter buttons | Button shows label 'L0 Data' (not 'Rejected'); clicking it queries status=rejected | Not Run | Critical | Key change in v2
TC-HDR-09 | Filter Buttons — Updated Labels | 'On Hold' button on Landing page now uses yellow (#ca8a04 / #dbbc23) color scheme | 1. Observe the 'On Hold' filter button | On Hold button accent is yellow (#dbbc23 active, #ca8a04 border); was purple in v1 | Not Run | High | Color scheme changed from purple to yellow
TC-HDR-10 | Filter Buttons — Age | Age filter colors updated: <3 Days uses emerald green (#10b981 active) | 1. Click '< 3 Days' filter | Active state background is #10b981 (emerald green), dot turns white | Not Run | Medium | AGE_FILTERS colors refreshed in v2

## RecordList
RecordList — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-VRL-01 | Initial Load | Full-page Loader shown when list is empty and loading | 1. Open any list page | Loader spinner shown immediately; disappears once first records arrive | Not Run | High
TC-VRL-02 | Infinite Scroll | Scrolling near bottom loads next page of records | 1. Scroll to near the bottom | Additional records appended; bottom loader briefly visible | Not Run | Critical
TC-VRL-03 | Count Label | 'Total records: N' label shown when showCount is true | 1. Observe above the record list | 'Total records: <N>' displayed for pages with age or status filters | Not Run | Medium
TC-VRL-04 | Row Heights | Accepted/Approved cards: height 100; pending cards: height 160 | 1. Compare card heights in a list with both accepted and pending records | Accepted cards visually shorter (no Inconsistent Fields section); pending cards taller | Not Run | Medium
TC-VRL-05 | Empty State | Empty message shown when no records and not loading | 1. Apply filter returning 0 records; 2. Wait for load to finish | Centered h6 message appears: 'No records match the selected filter.' | Not Run | High

## RecordCard
RecordCard — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-RCD-01 | Display | Card displays ExecutionID, BenchmarkCategory, BenchmarkType, Status | 1. Observe any record card | All four data labels and values visible | Not Run | Critical
TC-RCD-02 | Status Label — L0 Data | Records with status='rejected' show 'L0 Data' as the status text on the card | 1. Find a record with Status='Rejected' | Card status field shows 'L0 Data' (not 'Rejected') — display renamed in RecordCard | Not Run | Critical | Key UX change in v2: record.Status === 'rejected' -> displays 'L0 Data'
TC-RCD-03 | Card Background | All cards have white (#ffffff) background regardless of status | 1. Compare card backgrounds across statuses | All cards are #ffffff; differentiation comes from left border color only | Not Run | High | Background no longer uses status tinted colors; simplified to white
TC-RCD-04 | Card Border — Pending | Pending card has orange (#ffae00) left border (6px) and outer border (1.3px) | 1. Observe pending card borders | 6px left border (#ffae00); 1.3px full border (#ffae00); white background | Not Run | High
TC-RCD-05 | Card Border — Accepted | Accepted card has green (#10b981) border | 1. Observe accepted card borders | Green (#10b981) 6px left border; 1.3px outer border | Not Run | High
TC-RCD-06 | Card Border — On Hold | On Hold card has yellow (#f1e60b) border | 1. Observe on-hold card borders | Yellow (#f1e60b) 6px left border; 1.3px full border | Not Run | High | Changed to yellow from purple in v2
TC-RCD-07 | Card Border — L0 Data (Rejected) | L0 Data (rejected) card has red (#ef4444) border | 1. Find a record with Status=Rejected (shown as L0 Data) | Red (#ef4444) 6px left border | Not Run | High
TC-RCD-08 | Card Hover | Card hover: translateY(-4px) lift with shadow | 1. Hover over a card | Card lifts 4px (was 4px scale in v1) and shows colored shadow; cursor changes to pointer | Not Run | Medium | Hover changed from scale(1.02) to translateY(-4px)
TC-RCD-09 | Inconsistent Fields | Non-completed records show Inconsistent Fields chip list | 1. Observe a pending card | Divider below main info; red error chips listing invalid field names | Not Run | High
TC-RCD-10 | Suggestions Available Badge | Pending records with suggestions show 'Suggestions available' italic label | 1. Find a pending card that has suggestions | Italic text 'Suggestions available' visible in the Inconsistent Fields section (space-between row with chips) | Not Run | High | New in v2: SuggestionsCount prop passed to InconsistentFieldsList
TC-RCD-11 | Suggestions Available Badge | Pending records without suggestions do NOT show 'Suggestions available' | 1. Find a pending card with no suggestions | No 'Suggestions available' label present | Not Run | High
TC-RCD-12 | Accepted/Approved | Accepted/Approved cards do NOT show Inconsistent Fields section | 1. Find accepted card | No divider or chip list below main info row | Not Run | High
TC-RCD-13 | Navigation | Clicking a card navigates to DetailsPage for that record | 1. Click any card | Route changes to /<ExecutionId>; DetailsPage loads | Not Run | Critical

## DetailsPage
DetailsPage — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-DET-01 | Loading | Full Loader shown while fetching record details | 1. Click a card; observe immediately | Full-page Loader spinner shown until data arrives | Not Run | High
TC-DET-02 | Error Handling | ErrorPage with Retry shown on API failure | 1. Simulate API failure; open a record | ErrorPage component renders with error message and Retry button | Not Run | High
TC-DET-03 | Fallback | Plain text fallback if executionData is null | 1. Response has no execution_details field | Text 'No execution data to show' rendered (not a crash) | Not Run | Medium
TC-DET-04 | Snackbar — Success | Green success snackbar appears at top-center after accepting a suggestion | 1. Select suggestion; 2. Click Accept; 3. Confirm in dialog | Snackbar: 'Data accepted successfully' — green filled, top-center | Not Run | Critical
TC-DET-05 | Snackbar — Error | Red error snackbar appears on API failure during accept | 1. Simulate API error; attempt accept | Red snackbar with API error message | Not Run | High
TC-DET-06 | Snackbar — Draft | Success snackbar shown after successful draft record submission | 1. Fill draft form; submit | Green snackbar: 'Draft record submitted successfully' | Not Run | High | New flow in v2
TC-DET-07 | Snackbar — L0 | Success snackbar shown after sending to L0 | 1. Click 'Send to L0'; confirm | Green snackbar: 'Rejected due to L0 data' | Not Run | High
TC-DET-08 | Snackbar | Snackbar auto-dismisses after 3 seconds | 1. Trigger any action snackbar; wait 3s | Snackbar disappears automatically | Not Run | Medium

## ExecutionInfoBox
ExecutionInfoBox — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-EIB-01 | Layout | Execution info displays in a 3-column grid on desktop | 1. Open a record's detail page on desktop | ExecutionInfoBox shows 3 fields per row | Not Run | High
TC-EIB-02 | Layout | Grid collapses to single column on mobile (<md breakpoint) | 1. Resize to 375px width | Fields stack vertically | Not Run | Medium
TC-EIB-03 | Display | Null/undefined field values display as '-' | 1. Open record with null execution info fields | Null values show '-' (hyphen) | Not Run | Medium

## CorrectionsTable
CorrectionsTable — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-COR-01 | Empty State | Shows 'No invalid fields found.' when data is empty | 1. Open a fully-clean record | Centered gray text 'No invalid fields found.' shown | Not Run | High
TC-COR-02 | Group Expansion | Pending groups auto-expand; non-pending groups auto-collapse on load | 1. Open a record with both pending and accepted groups | Pending groups are expanded; accepted/on-hold/L0 groups are collapsed by default | Not Run | Critical | New in v2: expandedGroups initialized based on isPending status
TC-COR-03 | Group Accordion | Clicking collapsed group header expands it | 1. Click on the group header | Group body expands with collapse animation; icon changes to ExpandLess | Not Run | High
TC-COR-04 | Group Accordion | Clicking expanded group header collapses it | 1. Click on the group header | Group body collapses; icon changes to ExpandMore | Not Run | High
TC-COR-05 | Status Chips — Pending | 'Pending' chip shown in group header for pending/invalid fields | 1. Open a pending record, look at group header | Orange 'Pending' chip visible (#fff7ed background, #9a3412 text) | Not Run | High | New in v2: Pending chip added to group header
TC-COR-06 | Status Chips — L0 Data | 'L0 Data' red chip in header when field status is 'l0 data' | 1. Open record with L0 field | Red 'L0 Data' chip (#fef2f2 bg, #dc2626 text, #fca5a5 border) in header | Not Run | Medium
TC-COR-07 | Status Chips — On Hold | 'On Hold' chip is now yellow (not purple) in header | 1. Open on-hold record group header | Yellow 'On Hold' chip (#fef9c3 bg, #ca8a04 text, #fde047 border) | Not Run | High | Color changed from purple to yellow in v2
TC-COR-08 | Status Chips — Accepted | 'Accepted' chip + 'Suggestion Selected'/'Custom...' chip shown for accepted fields | 1. Open accepted group header | Green 'Accepted' chip and secondary chip indicating selection type | Not Run | High
TC-COR-09 | Suggestions Header | 'Suggestions' label only shown when suggestions exist; includes italic hint for pending | 1. Open pending group with suggestions | Label reads: 'Suggestions (Hover over an option to see confidence score)' | Not Run | Medium | New hint text added in v2
TC-COR-10 | Suggestions Header | Hints text NOT shown for accepted/on-hold groups | 1. Open accepted group | No italic hint text in the Suggestions label | Not Run | Medium
TC-COR-11 | Draft Records Section | Draft Record section shown below suggestions when group.draft_records exists | 1. Open an on-hold record that has a draft_records object | 'Draft Record' label and a read-only SuggestionRow (no radio) displayed with ON_HOLD_THEME | Not Run | Critical | New in v2: draft_records display for On Hold fields
TC-COR-12 | Draft Records Section | Draft Record SuggestionRow has no radio button (showRadio=false) | 1. Inspect Draft Record row | No radio button on the left; row is read-only display | Not Run | High | showRadio prop newly added in v2
TC-COR-13 | Draft Records Section | VM draft records show History CPU(s) value override | 1. Open VM on-hold record with CPU(s) history | Draft record SuggestionRow shows CPU(s) value from history, not from draft_records | Not Run | High | VM CPU(s) override logic applied to draft display
TC-COR-14 | Action Buttons | Three action buttons shown for pending groups: Accept, Submit Draft Record, Send to L0 | 1. Open pending group, observe action bar | Green 'Accept', yellow 'Submit Draft Record', red 'Send to L0' buttons visible | Not Run | Critical | Old 'Reject All' replaced by two separate actions in v2
TC-COR-15 | Action Buttons | 'Accept' button disabled when no suggestion selected | 1. Observe Accept button | Accept button is disabled (grayed out) | Not Run | Critical
TC-COR-16 | Action Buttons | 'Submit Draft Record' and 'Send to L0' disabled when a suggestion IS selected | 1. Select any suggestion; observe the other two buttons | Submit Draft Record and Send to L0 are disabled | Not Run | Critical | Mirrors old 'Reject All' disabled logic
TC-COR-17 | Action Buttons | All action buttons hidden for non-pending fields | 1. Open non-pending group | No action button bar rendered | Not Run | High
TC-COR-18 | Accept Confirm Dialog | Clicking Accept opens 'Confirm Accept' dialog | 1. Click 'Accept' | Dialog opens with green check icon, field name highlighted, Cancel and 'Yes, Accept' buttons | Not Run | Critical
TC-COR-19 | Accept Confirm Dialog | 'Yes, Accept' shows spinner + 'Accepting...' while API is in-flight | 1. Click 'Yes, Accept' | Button shows CircularProgress spinner with 'Accepting...' text; button disabled | Not Run | High
TC-COR-20 | L0 Confirm Dialog | Clicking 'Send to L0' opens standalone L0 Confirm dialog | 1. Click 'Send to L0' | Dialog: 'Confirm Send to L0', warning amber icon, 'Yes, Confirm' (warning color) and Cancel | Not Run | Critical | L0 dialog now standalone in CorrectionsTable (not nested in RejectDialog)
TC-COR-21 | L0 Confirm Dialog | L0 dialog: clicking X or Cancel during submission is disabled | 1. Click 'Yes, Confirm'; immediately try to close | Dialog cannot be closed while submitting (disabled state) | Not Run | High
TC-COR-22 | Draft Dialog | Clicking 'Submit Draft Record' opens Draft Record dialog with dynamic fields | 1. Click 'Submit Draft Record' | Dialog opens titled 'Submit Draft Record'; spinner shown while fields load from API; fields appear after | Not Run | Critical
TC-COR-23 | Draft Dialog | Draft dialog pre-fills field values from history changes | 1. Open Draft dialog for a field that has history | Form fields pre-populated with history values (from buildDisplayObjectFromChanges) | Not Run | High | New in v2: draftInitialValues from history
TC-COR-24 | Draft Dialog | Integer-type fields render as number inputs with step=1, min=0 | 1. Open draft dialog; inspect integer fields | Text field type='number', inputProps step=1 min=0; label shows '(integer)' hint | Not Run | High | New in v2: integer fields get type=number
TC-COR-25 | Draft Dialog | Submit disabled until all fields are non-empty | 1. Observe Submit button | Submit button disabled; enables only after all fields have non-whitespace values | Not Run | High
TC-COR-26 | Draft Dialog | Integer validation: error snackbar if non-integer value entered in integer field | 1. Type '2.5' in an integer field; 2. Click Submit | Error snackbar: 'The following fields require whole-number (integer) values: <fieldname>' | Not Run | High | New in v2: client-side integer validation before submit
TC-COR-27 | Draft Dialog | 'Submit Draft Record' payload sets currentStatus='On Hold' | 1. Submit a valid draft form; 2. Inspect API payload | POST to /draft-records/<field> with execution_id, form values, currentStatus='On Hold' | Not Run | High
TC-COR-28 | VM CPU(s) Override | For VM sutType, accepted suggestion shows CPU(s) from history (not suggestion raw data) | 1. Select suggestion in VM record with CPU(s) history | CPU(s) field in SuggestionRow shows history value, displayed correctly | Not Run | High | getHistoryChangesForField logic; UI override in CorrectionsTable

## SuggestionRow
SuggestionRow — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-SGR-01 | Selection | Clicking a suggestion selects it; radio checked, row highlighted | 1. Click any suggestion row | Radio checked; border and background change to SELECTED theme (blue) | Not Run | Critical
TC-SGR-02 | Selection | Clicking selected suggestion deselects it | 1. Click the selected suggestion | Radio unchecked; row returns to white background | Not Run | High
TC-SGR-03 | Confidence Tooltip | Hovering over suggestion shows 'Confidence: X%' tooltip | 1. Hover over a suggestion row | Tooltip appears: 'Confidence: X%' | Not Run | Medium
TC-SGR-04 | Internal Fields Filtered | Fields _id, execution_id, snapshot_id, search_key are hidden from suggestion display | 1. Open a suggestion row that has internal fields in data | None of _id, execution_id, snapshot_id, search_key appear as visible columns | Not Run | High | New in v2: internalKeys filter replaces old deduplication approach
TC-SGR-05 | showRadio prop | Draft Record SuggestionRow renders without radio button (showRadio=false) | 1. Observe Draft Record row | No radio button column on the left side of the row | Not Run | High | New showRadio prop in v2
TC-SGR-06 | EditableField — CPU(s) | CPU(s) field shows edit icon for VM sutType when suggestion selected | 1. Select suggestion in VM record group | Pencil edit icon visible next to the CPU(s) value | Not Run | High | Field changed from 'coreCount' to 'cpu(s)' in v2
TC-SGR-07 | EditableField — CPU(s) | Inline edit: click pencil, change value, press Enter to save | 1. Click pencil; change value; press Enter | New value shown; edit mode exits; value saved to editedSuggestions state | Not Run | High
TC-SGR-08 | EditableField — CPU(s) | Press Escape cancels inline edit and restores original value | 1. Click pencil; change value; press Escape | Original value restored; input closed | Not Run | High
TC-SGR-09 | Accepted/OnHold State | Non-pending suggestion rows are read-only (opacity 0.5, cursor not-allowed) | 1. Open accepted group, view suggestions | All suggestions dimmed (opacity 0.5); clicking does nothing (cursor: not-allowed) | Not Run | High

## ChooseOtherValueDropdown
ChooseOtherValueDropdown — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-CVD-01 | Visibility | Dropdown visible only for pending groups | 1. Expand a pending group | Autocomplete dropdown 'Choose other <field>:' is present | Not Run | High
TC-CVD-02 | Visibility | Dropdown hidden for non-pending groups | 1. Expand an accepted group | No dropdown rendered (isPending=false -> returns null) | Not Run | High
TC-CVD-03 | Options | Opening dropdown fetches unique masterlist values | 1. Click/open the autocomplete | Spinner appears; unique values from /unique-values API loaded as autocomplete options | Not Run | High
TC-CVD-04 | Selection | Selecting a value triggers metadata fetch and renders custom SuggestionRow | 1. Select a value | Dropdown row border turns accent color; 'Custom Value' label appears; SuggestionRow with fetched metadata shown | Not Run | Critical
TC-CVD-05 | Clear | Clearing autocomplete clears custom suggestion | 1. Clear the autocomplete (X button) | Custom SuggestionRow disappears; selection deactivated | Not Run | High
TC-CVD-06 | Theme Prop | Dropdown receives theme prop and applies activeTheme colors when selected | 1. Select a custom value | Dropdown row uses SELECTED theme border/background colors | Not Run | Medium | New theme prop passed in v2

## RejectDialog
RejectDialog — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-RJD-01 | Removed | RejectDialog component no longer exists as a separate file | 1. Check src/components/CorrectionsTableComponents/ directory | RejectDialog.jsx is NOT present; useRejectDialog.js hook is also removed | Not Run | Critical | BREAKING CHANGE: RejectDialog replaced by L0ConfirmDialog + DraftRecordDialog in v2

## L0ConfirmDialog
L0ConfirmDialog — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-RJD-02 | Standalone L0 Flow | L0 flow is now a direct dialog from the main action button bar | 1. Click 'Send to L0'; 2. Observe dialog | Single-step confirmation dialog (no multi-step choose flow); directly confirms L0 send | Not Run | Critical

## DraftRecordDialog
DraftRecordDialog — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-RJD-03 | Standalone Draft Flow | Draft flow is now a direct dialog from the main action button bar | 1. Click 'Submit Draft Record'; 2. Observe dialog | Direct Draft Record form dialog (no intermediate choose step) | Not Run | Critical

## ErrorPage
ErrorPage — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-ERR-01 | Display | ErrorPage renders with error message | 1. Simulate API error; open list page | ErrorPage renders with the error.message and a Retry button | Not Run | High
TC-ERR-02 | Retry | Retry button on ErrorPage triggers re-fetch | 1. Click Retry | Fetch is re-triggered; if API healthy, list loads normally | Not Run | High

## Loader
Loader — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-LDR-01 | Spinner | Loader renders centered spinner in all loading states | 1. Trigger loading (page load, record click, etc.) | Centered CircularProgress spinner visible; no layout breakage | Not Run | Medium

## Responsive
Responsive — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-RES-01 | Mobile (<768px) | Search bar adapts to 90% width on mobile | 1. Resize to 375px; observe search field | Width is ~90% of viewport; no overflow | Not Run | High
TC-RES-02 | Mobile (<768px) | Filter buttons wrap on narrow viewports | 1. Open /active on mobile | Filter buttons wrap to next line; no horizontal scrollbar | Not Run | High
TC-RES-03 | Tablet (768-1200px) | Record cards at 65vw readable on tablet | 1. Open list page at 768px wide | Cards at 65vw; text not clipped; cards centered | Not Run | Medium

## Cross-Browser
Cross-Browser — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-CBR-01 | Chrome | App renders and all flows work on Chrome (latest) | 1. Open app in Chrome; test all main flows | No rendering issues; all dialogs and cards render correctly | Not Run | Critical
TC-CBR-02 | Firefox | App works correctly on Firefox (latest) | 1. Open in Firefox; test main flows | No issues | Not Run | High
TC-CBR-03 | Edge | App works on Microsoft Edge | 1. Open app in Edge | No rendering or functionality issues | Not Run | Medium

## Performance
Performance — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-PER-01 | Load Time | List page shows first 50 records within 3 seconds | 1. Open /active; time to first record render | Records visible within 3 seconds | Not Run | High
TC-PER-02 | Search Debounce | Results update within 1 second after 500ms debounce | 1. Type in search; wait for debounce | API fires once; results update within 1s of debounce completing | Not Run | High
TC-PER-03 | Memory / Abort | Navigating between list pages aborts stale in-flight requests | 1. Quickly switch between /active and /completed several times | Only current page results shown; no ghost data; no console AbortError crashes | Not Run | High
TC-PER-04 | Animation Smoothness | Card hover and filter button transitions are smooth (no jank) | 1. Rapidly hover over cards and filter buttons | Transitions feel smooth; no flickering or layout shift | Not Run | Medium

## Accessibility
Accessibility — Test Cases
TC ID | Component | Test Case | Steps | Expected Result | Status | Priority | Remarks
TC-ACC-01 | Keyboard | Search field focusable via Tab key | 1. Tab to search; type query | Focus indicator visible; search works via keyboard | Not Run | High
TC-ACC-02 | Keyboard | Filter buttons activatable via keyboard (Space/Enter) | 1. Tab to filter button; press Space or Enter | Filter activates; list updates | Not Run | High
TC-ACC-03 | Contrast | All text meets WCAG AA contrast ratio (>=4.5:1) | 1. Run Lighthouse accessibility audit | All text passes AA contrast | Not Run | Medium
TC-ACC-04 | ARIA | Dialogs have ARIA role and focus trap | 1. Open Accept, L0, or Draft dialog; check ARIA | role='dialog'; focus trapped inside dialog while open | Not Run | Medium